## Sheet1
activity_name | zone | progress_percent | date | notes
Raft Foundation Reinforcement & Pour | Zone A | 85 | 2026-09-26 | Rebar layout 100% verified; concrete pour 85% completed
Diaphragm Wall & Piling | Zone A | 100 | 2026-09-26 | All 24 guide wall panels completed
Mass Excavation & Earthworks | Zone B | 45 | 2026-09-26 | Exhumed 4500 cu.m soil out of 10000 cu.m total target
Pier & Column Casting | Pier 4 | 30 | 2026-09-26 | Pier 4 shuttering complete; rebar cage placement under review