## Sheet1
activity_name | category | zone | planned_start | planned_end | status | unit | quantity
Diaphragm Wall & Piling | Substructure | Zone A | 2026-01-01 | 2026-03-31 | completed | panels | 24
Mass Excavation & Earthworks | Civil | Zone A | 2026-02-01 | 2026-04-30 | in_progress | cu.m | 10000
Raft Foundation Reinforcement & Pour | Concrete | Zone A | 2026-04-01 | 2026-06-30 | in_progress | cu.m | 2500
Base Slab Casting | Concrete | Zone B | 2026-05-01 | 2026-07-31 | not_started | cu.m | 3000
Pier & Column Casting | Structure | Pier 4 | 2026-06-01 | 2026-08-31 | in_progress | nos | 12
Facade Glazing & Curtain Wall | Finishes | Tower 1 | 2026-09-01 | 2026-11-30 | not_started | sq.m | 5000